PROJECT

NORTH STAR

Carrier-Grade VoIP Migration to AWS Connect

PROGRAM OVERVIEW

Section 1 of 10

Sprint 14 of 22  ·  July 2024  ·  Status: 🟡 AT RISK

Budget: $2.4M  ·  Duration: 11 months  ·  6,200 DIDs

# 1.1  Problem Statement

## The Situation

Acme Corp operates a Cisco Unified Communications Manager (UCM) 11.5 cluster hosted in a co-located data center in Ashburn, VA. The system manages all inbound and outbound telephony for the organization:

- 6,200 Direct Inward Dial (DID) numbers across sales, support, and operations

- 48 toll-free numbers used in customer-facing campaigns and support lines

- 34 IVR call flows handling an average of 12,000 inbound calls per day

- SIP trunking via Lumen Technologies (primary) and AT&T (backup)

## Three Converging Pressures

The legacy system faces simultaneous pressure from three directions:

1  END OF SUPPORT (EOS)

Cisco announced End of Software Maintenance for UCM 11.5 on December 31, 2024. Post-EOS operation creates unacceptable security exposure and directly jeopardizes our SOC 2 Type II certification renewal scheduled for Q1 2025.

2  OPERATIONAL COST

Annual total cost of ownership for the legacy PBX:

| Cost Component | Annual Cost |
| --- | --- |
| Cisco UCM maintenance contract | $142,000 |
| Co-location hosting (rack, power, cooling) | $88,000 |
| SIP trunk fees (Lumen + AT&T legacy rates) | $67,000 |
| Internal ops labor (Tier 2/3 support) | $43,000 |
| TOTAL ANNUAL COST | $340,000 |

AWS Connect at projected call volume is estimated at $96,000/year — a savings of $244,000 annually at full deprecation.

3  CAPABILITY CEILING

The legacy IVR has no analytics, no ML-based routing, and no CRM integration. Three of five top competitors have deployed AWS Contact Lens for intelligent routing and real-time CSAT measurement. Our platform cannot compete on customer experience features without this migration.

# 1.2  Business Impact

## Financial Analysis

| Scenario | 3-Year Cost | Notes |
| --- | --- | --- |
| Do nothing — maintain legacy | $1,020,000 | $340K/yr × 3 years |
| Migrate to AWS Connect (this program) | $2.69M one-time + $96K/yr | Migration cost + infra |
| Net 3-year savings post-migration | ~$450,000 | After break-even at Month 14 |

## Operational Impact

- Risk reduction: Elimination of single-datacenter-of-failure for all inbound calls

- Reliability: SLA improvement from 99.7% (Cisco UCM measured) to 99.9% (AWS Connect SLA)

- Scalability: Elastic capacity for call volume spikes and seasonal peaks

- Compliance: Maintains SOC 2 / PCI DSS alignment post-Cisco EOS

## Strategic Impact

- Unlocks AWS Contact Lens for ML-based agent coaching and CSAT measurement

- Enables Salesforce CTI integration (scoped for Phase 2)

- Reduces dependency on specialized Cisco CCIE talent for platform maintenance

- Creates the infrastructure foundation for AI-assisted routing planned in FY2025

# 1.3  Stakeholders

## RACI Matrix

| Stakeholder | Name | R | A | C | I |
| --- | --- | --- | --- | --- | --- |
| Executive Sponsor | Sarah Chen, VP Engineering | – | ✓ | – | – |
| Product Owner | Marcus Okafor, Dir. Product | ✓ | – | ✓ | – |
| Technical Program Manager | [TPM Name] | ✓ | ✓ | – | – |
| Lead Platform Engineer | Priya Nair, Staff Engineer | ✓ | – | – | – |
| Telecom Operations | James Whitfield, Sr. Mgr | ✓ | – | ✓ | – |
| QA Lead | Dana Kim, QA Lead | ✓ | – | – | – |
| Finance / FP&A | Tom Reyes, Sr. Analyst | – | – | ✓ | ✓ |
| CX / Contact Center | Diane Torres, Dir. CX | – | – | ✓ | ✓ |
| Security | Raj Patel, Sr. Security Eng | – | – | ✓ | – |

R = Responsible  ·  A = Accountable  ·  C = Consulted  ·  I = Informed

# 1.4  Program Phases

| Phase | Name | Duration | Status |
| --- | --- | --- | --- |
| Phase 0 | Discovery & Architecture Lock | Jan 2024 (4 wks) | ✅ Complete |
| Wave 1 | Dev/Staging Migration + ALB Cutover | Feb–Apr 2024 (10 wks) | ✅ Complete |
| Wave 2 | Production DID Block Porting | May–Sep 2024 (18 wks) | 🟡 In Progress |
| Wave 3 | Toll-Free + IVR Cutover | Oct–Nov 2024 (8 wks) | 🔴 At Risk |
| Phase 3 | Legacy PBX Decommission | Nov 2024 (2 wks) | ⏳ Planned |

# 1.5  Success Criteria

The program is considered successful when all of the following acceptance criteria are met:

| Criterion | Metric | Target | Owner |
| --- | --- | --- | --- |
| DID porting complete | DIDs operational on AWS Connect | 6,200 / 6,200 | James W. |
| Toll-free porting complete | TF numbers operational | 48 / 48 | James W. |
| IVR regression passed | Test coverage on call flows | ≥95% | Dana K. |
| SLA maintained post-cutover | Uptime for 30 days | ≥99.9% | Priya N. |
| Legacy PBX decommissioned | Cisco UCM hardware returned | 100% | James W. |
| IaC coverage | AWS Connect resources in Terraform | ≥90% | Priya N. |
| P1 tech debt resolved | Open P1 items in debt register | 0 open | TPM |
| Budget adherence | Final cost vs. $2.4M | Within 10% | Tom R. |

Next section: 01-architecture.md — System Architecture & Component Design