PROJECT NORTH STAR

Section 3 — Risk Management Framework

Risk Register  ·  Methodology  ·  Mitigation Playbooks  ·  Trend Analysis

Version 3.2  ·  Sprint 14  ·  July 2024  ·  Owner: TPM

# 3.1  Risk Management Methodology

## Risk Identification Channels

| Channel | Method | Frequency | Owner |
| --- | --- | --- | --- |
| Weekly risk review | Standing agenda item in Friday standup | Weekly | TPM |
| Pre-mortem sessions | Structured 'what could go wrong' before each wave | Per wave | TPM + leads |
| Dependency tracking | Automated Jira query for overdue dependency tasks | Daily | TPM |
| Retrospect findings | Risk items surfaced during sprint retrospects | Bi-weekly | Scrum team |
| Stakeholder escalations | Ad-hoc risks raised outside cadence | As needed | Any stakeholder |

## Risk Scoring Model — Likelihood × Impact

| Score | Likelihood | Impact |
| --- | --- | --- |
| 3 — High | Likely to occur this sprint/wave | Threatens schedule >2 wks, budget >$10K, or SLA |
| 2 — Medium | Possible within program timeline | Delays a deliverable, requires replanning |
| 1 — Low | Unlikely but plausible | Minor disruption, manageable within team |

## Severity Thresholds

| Score | Rating | Response Required |
| --- | --- | --- |
| 9 | CRITICAL | Immediate escalation to executive sponsor. Daily tracking. |
| 6 | HIGH | TPM mitigation plan within 24 hrs. Weekly exec update. |
| 4 | MEDIUM | Mitigation plan within 1 sprint. Bi-weekly review. |
| 1-2 | LOW | Monitor. Review monthly. |

# 3.2  Risk Register — Sprint 14 Snapshot

Total open risks: 11  ·  Critical: 2  ·  High: 2  ·  Medium: 4  ·  Low: 3  ·  Resolved: 2

| ID | Risk Description | Category | L | I | Severity | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R-001 | Carrier porting delay (Lumen) — LOA rejections, 90-day slip | Vendor | 3 | 3 | 9-CRIT | James W. | Mitigating |
| R-002 | IaC drift in AWS Connect — console changes vs Terraform state | Technical | 3 | 3 | 9-CRIT | Priya N. | In Progress |
| R-003 | CNAM vendor API not production-ready — real-time caller ID delayed | Vendor | 2 | 3 | 6-HIGH | James W. | Mitigating |
| R-004 | IVR regression coverage <80% — insufficient test coverage | Quality | 2 | 2 | 4-MED | Dana K. | In Progress |
| R-005 | AWS Connect usage overrun — Q2 pricing exceeded by 18% | Financial | 2 | 2 | 4-MED | Tom R. | Monitored |
| R-006 | Key SIP engineer attrition risk — 1 of 2 engineers interviewing | Staffing | 2 | 2 | 4-MED | Sarah C. | In Progress |
| R-007 | Wave 3 go-live blocked by Wave 2 slip — cascading delay | Schedule | 2 | 2 | 4-MED | TPM | Mitigating |
| R-008 | Cisco UCM EOS compliance gap if decommission slips past Dec 31 | Compliance | 1 | 3 | 3-LOW | Sarah C. | Monitored |
| R-009 | DID number loss during porting — incorrect LOA data | Technical | 1 | 3 | 3-LOW | James W. | Monitored |
| R-010 | AWS Connect service limit hit during peak | Technical | 1 | 2 | 2-LOW | Priya N. | Resolved |
| R-011 | Stakeholder misalignment on IVR greenfield scope | Scope | 1 | 2 | 2-LOW | TPM | Resolved |

L = Likelihood (1-3)  ·  I = Impact (1-3)  ·  Severity = L × I

# 3.3  Mitigation Playbooks

## R-001 — Carrier Porting Delay (CRITICAL)

Risk Statement: Lumen Technologies LOA processing delayed 90 days due to internal staffing backlog. Blocks Wave 2 DID porting and cascades to Wave 3.

| Action | Owner | Due Date | Status |
| --- | --- | --- | --- |
| Activate BYOC interim routing via Twilio | Priya N. | 2024-07-01 | Complete |
| Initiate parallel port with Bandwidth.com | James W. | 2024-07-10 | Complete |
| Replan Wave 2/3 schedule with revised dates | TPM | 2024-07-08 | Complete |
| Notify all stakeholders with impact analysis | TPM | 2024-07-03 | Complete |
| Weekly LOA status calls with Lumen | James W. | Ongoing | Active |
| Validate Bandwidth.com FOC dates weekly | James W. | Ongoing | Active |

## R-002 — IaC Drift in AWS Connect (CRITICAL)

| Action | Owner | Due Date | Status |
| --- | --- | --- | --- |
| Run terraform plan — identify all drift | Priya N. | 2024-07-15 | In Progress |
| Import drifted resources into Terraform state | Priya N. | 2024-07-22 | Planned |
| Apply SCP blocking console edits to Connect | Priya N. | 2024-07-19 | In Progress |
| Add terraform plan as required CI gate on PRs | Priya N. | 2024-07-12 | Complete |
| Document IaC-first policy in team runbook | TPM | 2024-07-15 | In Progress |

## R-006 — Key Engineer Attrition (MEDIUM)

| Action | Owner | Due Date | Status |
| --- | --- | --- | --- |
| Initiate comp review with HR | Sarah C. | 2024-07-12 | In Progress |
| Begin runbook documentation sprint | Priya N. | 2024-07-15 | In Progress |
| Cross-train second engineer on SIP config | Priya N. | 2024-08-01 | Planned |
| Identify contractor backup (CCIE-certified) | TPM | 2024-07-19 | Planned |

# 3.4  Risk Trend Analysis

| Sprint | Critical | High | Medium | Low | Total |
| --- | --- | --- | --- | --- | --- |
| Sprint 10 | 1 | 2 | 5 | 3 | 11 |
| Sprint 11 | 1 | 2 | 5 | 3 | 11 |
| Sprint 12 | 2 | 2 | 4 | 3 | 11 |
| Sprint 13 | 2 | 2 | 4 | 3 | 11 |
| Sprint 14 (now) | 2 | 2 | 4 | 3 | 11 |

Trend: Critical risks increased Sprint 10→12 when R-002 (IaC drift) was identified. Two risks resolved since Sprint 10. No net reduction — Wave 2 complexity generating new risks at same rate as closures. Target: 1 critical, 2 high by Sprint 16.

Next section: Dependency Management →  dependency-log.md