PROJECT NORTH STAR

Section 7 — Scope Creep Control

Governance Model  ·  Change Register  ·  CR-007 Full Scenario  ·  Impact Summary

Version 1.3  ·  Sprint 14  ·  8 CRs total  ·  6 deferred  ·  22+ weeks protected

# 7.1  Scope Governance Model

Scope creep doesn't announce itself. It arrives as reasonable requests from well-intentioned stakeholders. The TPM's job is not to say no to everything — it's to make the cost of every addition visible before it is accepted.

## Decision Criteria

| Criterion | Threshold | Action |
| --- | --- | --- |
| In approved charter? | Yes | Accept |
| Schedule impact | >2 weeks | Requires executive sponsor approval |
| Budget impact | >$10,000 | Requires executive sponsor approval |
| Blocks current go-live? | Yes | Escalate immediately |
| Can be phased post-MVP? | Yes | Defer to Phase 2 |
| Valid but out of scope | Any | Parking lot — Phase 2 charter |

# 7.2  Change Request Register

| CR | Submitted By | Request | Date | Sched Impact | Budget Impact | Decision |
| --- | --- | --- | --- | --- | --- | --- |
| CR-001 | Marcus Okafor | Salesforce CTI screen pop at Wave 3 | Feb 15 | + 8 weeks | +$45,000 | Deferred |
| CR-002 | Diane Torres | Real-time agent dashboard | Mar 8 | + 4 weeks | +$18,000 | Deferred |
| CR-003 | Priya Nair | Multi-region failover at Wave 1 | Mar 22 | + 6 weeks | +$18K/mo | Deferred |
| CR-004 | Sarah Chen | Accelerate Wave 3 — Lumen recovery | Jul 5 | - 4 weeks | +$4,200 | Accepted |
| CR-005 | Marcus Okafor | Contact Lens sentiment analysis | May 20 | + 3 weeks | +$8,000 | Deferred |
| CR-006 | Dana Kim | Expand regression to perf testing | Jun 10 | + 2 weeks | +$5,000 | Partially accepted |
| CR-007 | Marcus Okafor | Real-time analytics dashboard | Jun 18 | +6-8 weeks | +$38,000 | Deferred |
| CR-008 | James Whitfield | STIR/SHAKEN call authentication | Jul 2 | + 5 weeks | +$22,000 | Deferred |

# 7.3  Full Scenario — CR-007: Real-Time Analytics Dashboard

This is the most detailed example of scope creep management on Project NORTH STAR. It shows how a valid, well-intentioned request was handled without damaging the stakeholder relationship or the program timeline.

## The Request — June 18, 2024

"Hey — the CX team needs a real-time call analytics dashboard. Live call volume, queue depth, agent availability, and abandonment rate. They need this for Wave 3 go-live. I know it's more work but I think it's important. Can we scope it? I'm thinking it's a few weeks of work."

## Impact Assessment — June 20, 2024

| Impact Item | Detail |
| --- | --- |
| Engineering effort | 6–8 weeks (2 engineers) — NOT 'a few weeks' |
| Schedule impact | Wave 3 slips 6–8 weeks → Dec 15 to Feb 2025 |
| Budget impact | +$38,000 — infrastructure + engineering time |
| Dependencies added | Kinesis + QuickSight — 2 new AWS services not in current IaC scope |
| Risk introduced | New services = new drift risk, new security surface area |

## Decision Framework Applied

| Question | Answer | Implication |
| --- | --- | --- |
| In approved program charter? | No | Analytics explicitly listed as Phase 2 work in January charter |
| Blocks Wave 3 go-live? | No | Connect native reporting covers core use case for 90 days |
| Can be phased post-Wave 3? | Yes | CTR Kinesis stream already being built in Wave 2 — dashboard layer only |
| Business risk of 90-day deferral? | Low | CX has no real-time analytics today — any dashboard is an improvement |

Decision: CR-007 DEFERRED — Wave 3 schedule protected, Phase 2 charter created

## Stakeholder Communication — June 21, 2024

EMAIL  ·  Sent within 48 hours of impact assessment

From: [TPM Name]  ·  To: Marcus Okafor  ·  Date: June 21, 2024

Subject: CR-007 Real-Time Analytics Dashboard — Impact Assessment + Decision

Marcus — here's the impact assessment I promised.

Engineering reality check: This is 6–8 weeks, not a few weeks. Kinesis, Lambda, QuickSight, S3 data lake. Priya's full estimate is attached.

If we accept: Wave 3 moves Dec 15 → Feb 2025. That's $57,000 in additional PBX costs we've been fighting to eliminate.

My recommendation: Defer CR-007 to Phase 2. Good news: the CTR streaming infrastructure is already being built in Wave 2. Phase 2 dashboard will be faster and cheaper because the hard part will already be done.

CX gets AWS Connect native reporting at Wave 3 go-live — covers core use case for first 90 days.

Wave 3 schedule is protected. No budget impact. Phase 2 charter stub created.

## Outcome

| Item | Result |
| --- | --- |
| Wave 3 schedule | Protected — no change |
| Budget | No impact |
| Stakeholder relationship | Preserved — Marcus: 'the right call' |
| CR-007 Phase 2 | Charter created — Priya assigned for Q4 2024 discovery |
| CX interim | AWS Connect native reporting briefed to Diane Torres |

# 7.4  Scope Protection Summary

| Outcome | Count | Notes |
| --- | --- | --- |
| Accepted | 1 | CR-004 — Option B carrier acceleration |
| Partially accepted | 1 | CR-006 — load testing accepted, perf suite deferred |
| Deferred to Phase 2 | 6 | All with Phase 2 charter or parking lot ticket created |
| Rejected outright | 0 | Every valid idea has a home — none were discarded |

Total scope protection: 6 change requests deferred, protecting an estimated 22+ weeks of schedule and $131,000+ in additional program costs.

Next section: AI Integration & Prompt Library →  ai-operations/prompt-library.md