PROJECT NORTH STAR

Section 9 — Execution Workflow

Operating Cadence  ·  Jira Structure  ·  Decision Flow  ·  Status Reporting  ·  Escalation

Version 1.1  ·  Sprint 14  ·  July 2024

# 9.1  Program Operating Cadence

## Weekly Rhythm

| Day | Activity | Duration | Participants | Output |
| --- | --- | --- | --- | --- |
| Monday | Dependency review — check Jira filter for overdue deps | 15 min | TPM solo | Updated dependency log |
| Tuesday | Engineering standup | 15 min | Priya, Dana, TPM | Blocker list |
| Wednesday | Carrier sync (James + Lumen/Bandwidth) | 30 min | James W., TPM | LOA status update |
| Thursday | Sprint ceremonies (bi-weekly) | 2 hrs | Full team | Completed stories, retro actions |
| Friday | Risk review + weekly status report | 45 min | TPM → Sarah async | Status report by 4pm ET |

## Sprint Structure

SPRINT START (Monday)

├── Sprint planning (2 hrs) — TPM + full team + Marcus Okafor

│   ├── Review carry-over from last sprint

│   ├── Capacity check (vacations, risk-driven reductions)

│   └── Debt allocation confirmed (15% minimum)

│

SPRINT MID (end of Week 1)

├── Mid-sprint check (15 min) — TPM + leads

│   ├── Blockers surfaced since planning?

│   └── Velocity on track?

│

SPRINT END (Friday Week 2)

├── Sprint review (1 hr) — full team + Marcus

├── Sprint retrospect (45 min) — engineering team

└── Status report sent → Sarah Chen

# 9.2  Jira Board Structure

## Automated Saved Filters

| Filter Name | Query | Used For |
| --- | --- | --- |
| Overdue Dependencies | label = dependency AND dueDate < now() AND status != Done | Monday review |
| P1 Debt Open | label = p1-debt AND status != Done | Sprint planning — must include |
| Blocked This Sprint | sprint in openSprints() AND status = Blocked | Daily standup |
| Decision Required | label = decision-required AND status != Done | Weekly sync |
| Wave 3 Readiness | fixVersion = Wave-3 AND status != Done | Go/No-Go tracking |

# 9.3  Decision-Making Flow

Not all decisions are equal. The framework below determines who owns what and how fast it moves.

| Decision Type | Owner | Timeline | Method |
| --- | --- | --- | --- |
| Reversible, <$5K | TPM | Same sprint | Document in register, inform async |
| Schedule >1 week or budget >$10K | TPM + Eng Lead | Within 48 hrs | Present options to Sarah for awareness |
| Go-live impact or budget >$50K | Sarah Chen | Within 24 hrs | Written options + Decision Register |
| Strategic or budget >$100K | CFO / CEO | TPM prepares case | Business case — Sarah escalates |

# 9.4  Status Reporting Flow

## RAG Status Criteria

| Status | Criteria |
| --- | --- |
| GREEN | On schedule ±1 week. No critical/high risks without active mitigation. Budget within 5%. |
| AMBER | Schedule slip 1-3 weeks OR 1 critical risk without full mitigation OR budget 5-10% over. |
| RED | Schedule slip >3 weeks OR 2+ critical risks OR budget >10% over OR go-live threatened. |

Rule: Status never moves from RED to GREEN in one week. It must pass through AMBER first. This prevents false optimism and maintains executive trust.

# 9.5  Wave Go/No-Go Gate — Wave 3 Example

| Gate | Criteria | Owner | Status |
| --- | --- | --- | --- |
| Technical | IaC coverage ≥90% for all Connect resources | Priya N. | Pending |
| Technical | All 34 IVR flows pass regression testing | Dana K. | Pending |
| Technical | Rollback tested in staging within 48hrs of cutover | Priya N. | Pending |
| Quality | IVR test coverage ≥80% | Dana K. | In Progress — 61% |
| Vendor | All toll-free numbers ported and confirmed | James W. | Pending |
| Monitoring | CloudWatch + PagerDuty alerts active | Priya N. | Pending |
| Sign-off | Sarah Chen written approval | Sarah C. | Pending |
| Sign-off | Marcus Okafor acceptance | Marcus O. | Pending |

# 9.6  Escalation Protocol

| Situation | Escalate To | Timeline | Method |
| --- | --- | --- | --- |
| Dependency slip >2 weeks | Sarah Chen | Within 24 hrs | Written impact analysis + options |
| Budget overrun >10% | Sarah Chen + Tom Reyes | Within 24 hrs | Written with cost-to-complete update |
| Critical risk — no mitigation | Sarah Chen | Same day | Slack + follow-up email |
| Key engineer departure | Sarah Chen + HR | Immediately | Phone + email |
| Production outage during cutover | Sarah Chen + Priya N. | Immediately | Phone — not Slack |
| Vendor contractual failure | Sarah Chen + Legal | Same day | Written with contract reference |

Golden rule: Sarah Chen should never hear about a problem first from someone other than the TPM. If a stakeholder raises an issue that hasn't been escalated yet, that is a program management failure.

Next section: Section 10 — Final Polish & README Update