PROJECT NORTH STAR

Section 4 — Dependency Management

Dependency Register  ·  Carrier Delay Scenario  ·  Replanning Options  ·  Stakeholder Comms

Version 2.3  ·  Sprint 14  ·  July 2024  ·  Owner: TPM

# 4.1  Dependency Management Methodology

A dependency is any external input, deliverable, or decision that must be completed before a program workstream can proceed. On Project NORTH STAR, dependencies fall into four categories:

| Category | Examples | Risk Level |
| --- | --- | --- |
| External Vendor | Carrier LOA processing, CNAM API readiness, AWS limits | HIGH |
| Internal Team | QA coverage gates, IaC drift remediation, security reviews | MEDIUM |
| Platform / Infra | AWS Connect limits, Terraform state migration | LOW |
| Decision / Approval | Executive sign-off on scope changes, budget approvals | MEDIUM |

# 4.2  Dependency Register — Sprint 14

| ID | Dependency | Type | Owner | Due Date | Status | Blocks |
| --- | --- | --- | --- | --- | --- | --- |
| DEP-001 | Lumen LOA processing — 2,358 DID block | Vendor | James W. | 2024-07-05 | 🔴 DELAYED +90d | Wave 2 porting |
| DEP-002 | Bandwidth.com contract execution | Vendor | James W. | 2024-07-10 | ✅ Complete | DEP-001 mitigation |
| DEP-003 | CNAM vendor API production readiness | Vendor | James W. | 2024-08-01 | 🟡 At Risk | Wave 3 CNAM |
| DEP-004 | IVR regression coverage ≥80% | QA | Dana K. | 2024-09-15 | 🟡 In Progress | Wave 3 gate |
| DEP-005 | Terraform state migration to S3 | Infra | Priya N. | 2024-07-19 | 🟡 In Progress | IaC team access |
| DEP-006 | SCP console-change blocking policy | Infra | Priya N. | 2024-07-22 | 🟡 In Progress | R-002 fix |
| DEP-007 | AWS Connect service limit increase | Platform | Priya N. | 2024-06-20 | ✅ Complete | Wave 2 volume |
| DEP-008 | Executive approval — Option B replan | Decision | Sarah C. | 2024-07-05 | ✅ Complete | Wave 2 replan |
| DEP-009 | Runbook documentation — SIP config | Staffing | Priya N. | 2024-08-01 | 🟡 In Progress | R-006 mitigation |
| DEP-010 | Wave 3 go/no-go gate approval | Decision | Sarah C. | 2024-10-01 | ⬜ Planned | Wave 3 cutover |

# 4.3  Critical Scenario — DEP-001: Lumen Carrier Delay

## Background

On June 28, 2024, James Whitfield received informal notice from the Lumen Technologies account manager that our LOA submission for 2,358 DID numbers had been flagged for manual review. On July 1, formal written confirmation was received: 90-day delay on LOA processing.

## Impact Analysis

Wave 2 Direct Impact

| Milestone | Original Date | Revised Date | Slip |
| --- | --- | --- | --- |
| Wave 2 DID porting complete | 2024-07-05 | 2024-09-30 | +87 days |
| DIDs operational on AWS Connect | 2024-07-05 | 2024-10-01 | +88 days |

Cascading Impact

| Milestone | Original Date | Revised Date | Slip |
| --- | --- | --- | --- |
| Wave 3 (TF + IVR) go-live | 2024-09-01 | 2024-12-15 | +105 days |
| Legacy PBX decommission | 2024-10-15 | 2025-01-15 | +92 days |
| Annual savings realization | 2025-01-01 | 2025-04-01 | +90 days |

Financial Exposure (without mitigation)

| Cost Item | Amount | Notes |
| --- | --- | --- |
| Additional PBX operation — 3 months | $85,500 | $28,500/mo × 3 months |
| Option B — Bandwidth.com parallel port | $4,200 | One-time contract + porting fees |
| Delayed savings realization | $61,000 | $244K/yr × 3/12 months delayed |
| Total exposure without mitigation | $150,700 | Net cost of inaction |

## Replanning Options

Option A — Accept Slip, Compress Downstream

| Factor | Detail |
| --- | --- |
| Schedule recovery | ~6 weeks (partial compression) |
| Cost | +$32,000 (contractor 8 weeks) |
| Risk | HIGH — team at capacity, parallel workstreams increase coordination overhead |
| Dependency | Lumen remains single carrier — slip could extend further |

Option B — Dual-Carrier Parallel Port ✅ SELECTED

| Factor | Detail |
| --- | --- |
| Schedule recovery | ~4 weeks (Wave 2 completion Sep 30 vs. Jul 5) |
| Cost | +$4,200 one-time — Bandwidth.com contract + porting fees |
| Risk | LOW — Bandwidth.com avg LOA processing 15 days vs. Lumen 90+ |
| Dependency | Permanently eliminates single-carrier risk |

Option C — Escalate to Lumen Executive Contacts

| Factor | Detail |
| --- | --- |
| Schedule recovery | Unknown — depends on Lumen responsiveness |
| Cost | $0 |
| Risk | HIGH — no guarantee, puts program at mercy of vendor politics |
| Dependency | Still single-carrier dependent |

## Decision — Option B Selected

| Field | Detail |
| --- | --- |
| Decision date | July 5, 2024 |
| Decision maker | Sarah Chen — VP Engineering |
| Recommended by | [TPM Name] |
| Decision Register | DR-007 |
| Rationale | $4,200 cost negligible vs. $85,500 exposure. Dual-carrier also permanently reduces architectural risk flagged in Wave 1 planning. |

## Stakeholder Communication — July 3, 2024

EMAIL  ·  Sent 48 hours after confirmation  ·  2 days before decision meeting

From: [TPM Name]

To: Sarah Chen, Marcus Okafor, Tom Reyes

CC: James Whitfield, Priya Nair

Date: July 3, 2024

Subject: [NORTH STAR] Wave 2 Schedule Impact — Lumen Carrier Delay Confirmed + Options

Hi team,

I want to get ahead of an issue confirmed this week before it becomes a surprise in our next status report.

What happened: Lumen Technologies has formally notified us of a 90-day delay on our DID block LOA processing. FOC date moves from July 5 → October 3.

What this means: Wave 2 completion July 5 → September 30. Wave 3 go-live September 1 → December 15. Legacy PBX decommission moves to January 2025. Additional PBX costs: $85,500.

Good news: Inbound calls are NOT affected. BYOC interim routing is active. All 12,000 daily calls routing normally.

Recommendation: Option B — parallel DID port with Bandwidth.com. Cost: $4,200 one-time. Recovery: ~4 weeks. Eliminates single-carrier risk permanently.

Ask: 30-minute sync with Sarah and Tom by Friday EOD to authorize Option B. Revised Gantt and cost-to-complete projection ready by Thursday EOD.

— [TPM Name]

## Post-Decision Actions

| Action | Owner | Status |
| --- | --- | --- |
| Bandwidth.com contract executed | James W. | Complete 2024-07-08 |
| Revised program schedule published | TPM | Complete 2024-07-08 |
| Risk register updated (R-001, R-007) | TPM | Complete 2024-07-08 |
| Decision Register entry DR-007 created | TPM | Complete 2024-07-08 |
| Weekly Lumen LOA status calls initiated | James W. | Active — ongoing |
| Bandwidth.com port scheduled Aug 15 | James W. | Complete 2024-07-10 |

Next section: Technical Trade-offs →  docs/04-technical-tradeoffs.md