PROJECT NORTH STAR

Section 8 — AI Integration & Prompt Library

6 Production Prompts  ·  Claude AI  ·  Status Reports  ·  Risk Analysis  ·  Sample Output

Version 1.2  ·  Sprint 14  ·  July 2024

# 8.1  AI Integration Philosophy

Claude AI is used on Project NORTH STAR for three specific functions:

| Function | What It Does | What It Doesn't Do |
| --- | --- | --- |
| Acceleration | First drafts of reports, analyses, and comms in <60 seconds | Make decisions — every output is TPM-reviewed and owned |
| Pattern Recognition | Surface risks buried in sprint data, dependency logs, meeting notes | Replace engineering judgment on architecture decisions |
| Consistency | Ensure every report and risk entry follows the same structure | Substitute for stakeholder relationships — AI drafts, humans send |

# 8.2  Prompt Library — 6 Production Prompts

Prompt 1 — Weekly Status Report Generator

Use case: Every Friday — produces first-draft status report in <60 seconds. TPM edits for 10 min vs. writing from scratch (45 min).

You are a senior TPM writing a weekly status report for VP Engineering and Director of Product.

Format:

## Overall Status: [RED / AMBER / GREEN]

One sentence justification — name the specific risk or blocker.

## Accomplishments This Week (max 3 bullets, reference specific stories)

## Active Risks (top 2 only, flag CRITICAL/HIGH explicitly)

## Decisions Needed from Leadership (only if a decision is genuinely needed)

## Next Week Focus (3 bullets with owners)

Rules: Direct. No fluff. No passive voice. Reader has 90 seconds.

Never say 'we are working on' — say what will be done and by when.

SPRINT DATA: velocity={pts}/{target}, completed={stories}, blockers={blockers}

RISKS: {top_risks_csv}

Prompt 2 — Risk Spotter

Use case: After sprint reviews or stakeholder meetings — identifies missed or under-weighted risks from meeting notes.

You are a risk analyst for a complex cloud infrastructure program.

Review the update below. Identify risks the TPM may have missed.

For each risk:

1. Likelihood (High/Med/Low) and Impact (High/Med/Low)

2. Root cause category: [Vendor|Technical|Staffing|Scope|Compliance|Financial]

3. ONE concrete mitigation action (not vague)

4. Flag dependencies on other open risks

Focus on: upstream dependencies mentioned casually, single points of failure,

unowned action items, timeline compression, 'we'll figure it out later' language.

Output: Markdown table — Risk|Category|Likelihood|Impact|Mitigation|Dependencies

UPDATE: {paste_meeting_notes_here}

Prompt 3 — Dependency Slip Analyzer

Use case: When a critical dependency slips — produces impact analysis and stakeholder comm draft. Used for DEP-001 Lumen delay.

A critical dependency has slipped by {N} weeks.

Dependency: {description} | Blocked: {workstreams} | Status: {rag}

Produce:

1. PLAIN LANGUAGE IMPACT (3-4 sentences, no jargon)

What slipped, what it blocks, financial exposure, what is NOT affected.

2. THREE REPLANNING OPTIONS (comparison table)

Per option: approach, schedule recovery, cost delta, risk, dependency

3. RECOMMENDATION with rationale (2-3 sentences)

4. DRAFT STAKEHOLDER EMAIL

Para 1: What happened (factual) | Para 2: Program impact (dates + costs)

Para 3: Recommendation and why | Para 4: Specific ask with deadline

Tone: Calm, factual, solution-oriented. Never say 'unfortunately'.

Prompt 4 — Technical Debt Triage

Use case: Quarterly Debt Day — ranks debt backlog by impact score and recommends sprint assignments.

Score the technical debt backlog below.

For each item:

- Security Risk (1-5): 5=SOC2 blocker, 3=potential exposure, 1=minimal

- Delivery Risk (1-5): 5=blocks next wave, 3=operational risk, 1=cosmetic

- Effort (1-5): 5=highest effort

Priority Score = (Security x 2) + (Delivery x 2) - Effort

Output:

1. Ranked table: ID|Item|Sec|Del|Eff|Score|Priority(P1/P2/P3)

2. Sprint assignments for top 5 items

3. Items to ESCALATE to executive sponsor (security findings)

4. Items to CLOSE without fixing (no longer relevant)

BACKLOG: {paste_debt_items_here}

Prompt 5 — Scope Change Impact Assessment

Use case: 48-hour impact assessment for every change request. Used directly for CR-007 analytics dashboard.

A stakeholder has requested: "{scope_change_request}"

Submitted by: {name} ({role}) | Program: Sprint {N}/{total}, {status}

Evaluate using this framework:

1. IN SCOPE? (Yes/No/Partially) — reference the program charter

2. ENGINEERING EFFORT — provide a range, flag if estimate seems off

3. SCHEDULE IMPACT — accepted now vs. deferred 90 days

4. CAN IT BE PHASED? — v1 now, full delivery later? Interim for users?

5. BUSINESS RISK OF DEFERRAL — immediate or theoretical?

6. RECOMMENDATION — Accept/Defer/Reject with one-paragraph rationale

Output: One-page decision brief for a 15-minute stakeholder review.

A non-engineer must understand the trade-off immediately.

Prompt 6 — Pre-Wave Go/No-Go Checklist

Use case: 2 weeks before each wave cutover — generates customized checklist based on current program state.

Generate a Wave {N} go/no-go checklist.

Wave: {description} | Dependencies: {deps} | Risks: {risks}

Rollback window: {window} | Sign-off required: {stakeholders}

Produce three sections:

PRE-CUTOVER (T-5 days to T-1 hour)

- Technical gates: IaC validated, monitoring active, rollback tested

- Business gates: notifications sent, support team briefed

- Vendor gates: carrier confirmation, SIP test calls completed

DURING CUTOVER (T-0 to T+2 hours)

- Go/no-go decision criteria (specific and measurable)

- Escalation contacts | Rollback trigger conditions

POST-CUTOVER (T+2 to T+24 hours)

- Validation checks | Monitoring thresholds | Stakeholder notification

Each item: checkbox + owner + time gate + pass/fail criteria.

No vague items. 'Confirm everything is working' is not acceptable.

# 8.3  Sample AI Output — Sprint 14 Status Report

The following is an actual Claude-generated status report draft produced using Prompt 1, before TPM editing. Time to generate: 8 seconds.

CLAUDE OUTPUT — UNEDITED FIRST DRAFT

Overall Status: AMBER

Wave 2 remains on revised schedule (Sep 30) after Lumen mitigation, but R-002 (IaC drift)

is overdue and Sprint 14 velocity (34 pts) is below target (42) for the second sprint.

Accomplishments:

- DID webhook handler deployed — port status events flowing to DynamoDB in real time

- Secrets Manager IAM policy scoped — TD-001 remediation 60% complete

- Bandwidth.com FOC confirmed for Aug 15 — Wave 2 recovery on track

Active Risks:

R-002 | IaC drift — Terraform audit in progress, SCP blocked on AWS support | Priya N. | S15

R-006 | Attrition risk — comp review pending HR | Sarah C. | Jul 19

Decision Needed:

Sprint 15 capacity: Feature work vs. debt sprint → Recommend debt sprint (43% to P1 items)

Needed by: Jul 15 sprint planning

Next Week:

- Priya N.: Complete Terraform S3 migration (TD-003)

- James W.: Confirm Bandwidth.com Aug 15 port batch details

- TPM: Sprint 15 planning — align Marcus on reduced feature capacity

Next section: Execution Workflow →  docs/03-execution-workflow.md