PROJECT NORTH STAR

Section 5 — Technical Trade-offs

3 Engineering vs. Product Decisions  ·  Context  ·  Options  ·  Outcomes

Version 1.4  ·  Sprint 14  ·  July 2024

# 5.1  Trade-off Framework

Every trade-off on this program was evaluated using four questions before a decision was made:

- What is the delivery risk if we do this now? — Schedule, quality, or stability impact

- What is the business risk if we defer this? — Revenue, compliance, or customer impact

- Can it be phased? — Is there a version that ships now with a clear path to full delivery later?

- Who accepts the risk in writing? — Every decision is owned by a named person in the Decision Register

No trade-off was made verbally. Every decision below is in the Decision Register with a named owner.

# 5.2  Trade-off #1 — Real-Time CNAM vs. On-Time Wave 3

| Field | Detail |
| --- | --- |
| Decision date | June 15, 2024 |
| Decision maker | Marcus Okafor (Product) — accepted engineering recommendation |
| Decision Register | DR-005 |

The Tension

| Engineering Position | Product Position |
| --- | --- |
| Defer CNAM — API unstable | Ship real-time CNAM with Wave 3 |
| Vendor API is not load-tested, has no SLA, and has no fallback. Shipping it introduces P1 call failure risk for all toll-free callers. | 12% of enterprise prospects specifically ask about CNAM. Delay puts us behind Competitor X who launched in June. |

Options Evaluated

| Option | Schedule | Quality Risk | Business Risk |
| --- | --- | --- | --- |
| A — Ship real-time CNAM now | None | HIGH — API unstable | Low |
| B — Defer CNAM entirely to Q1 2025 | None | None | HIGH — 6-month gap |
| C — Static now, real-time Q1 2025 ✅ | None | LOW — CSV reliable | LOW — feature ships |

Decision: Option C — Static CNAM at Wave 3, real-time CNAM in Q1 2025 (TD-007)

Why product accepted: Engineering provided a written risk assessment confirming zero SLA impact for 90 days. TPM framed it as 'the feature ships — it just doesn't update in real time yet.' Product briefed the sales team directly on the weekly refresh caveat.

# 5.3  Trade-off #2 — Multi-Region Failover vs. Cost Ceiling

| Field | Detail |
| --- | --- |
| Decision date | February 2, 2024 |
| Decision maker | Sarah Chen — VP Engineering |
| Decision Register | DR-004 (also ADR-004) |

The Tension

| Engineering Position | Product Position |
| --- | --- |
| Active-active multi-region | Single-region — budget constraint |
| AZ failure = total call failure. 4-hour blast radius unacceptable for customer-facing system. Active-active (us-east-1 + us-west-2) provides ~15 min recovery. | $18,000/month ($216K/year) for multi-region requires board approval. Legacy PBX ran at 99.7% — even single-region is a major reliability improvement. |

Options Evaluated

| Option | Monthly Cost | Recovery Time | Complexity | Selected |
| --- | --- | --- | --- | --- |
| A — Single-region, Multi-AZ ✅ | $0 | ~4 hrs (AZ failure) | Low | Yes |
| B — Active-active multi-region | +$18,000 | ~15 min | High | FY2025 |
| C — Warm standby us-west-2 | +$6,500 | ~45 min | Medium | No |

Decision: Option A — Single-region (us-east-1) Multi-AZ with enhanced monitoring

Mitigations added: Route 53 health checks (30-sec detection), CloudWatch alarms at 99% threshold, PagerDuty P1 escalation, regional outage runbook. Risk formally accepted by Sarah Chen in writing.

# 5.4  Trade-off #3 — Greenfield IVR Rebuild vs. Lift-and-Shift

| Field | Detail |
| --- | --- |
| Decision date | January 28, 2024 |
| Decision maker | TPM facilitated — Marcus Okafor (Product) accepted |
| Decision Register | DR-002 |

The Tension

| Engineering Position | Product Position |
| --- | --- |
| Greenfield rebuild | Lift-and-shift — behavior parity |
| Legacy flows carry 11 years of undocumented debt. Greenfield enables AWS Connect ML routing and Contact Lens analytics from day one. | CX team has 4 live A/B tests on IVR. Greenfield breaks tested sequences. Requests zero behavior change until data supports it. |

Options Evaluated

| Option | Timeline | Quality | Business Impact |
| --- | --- | --- | --- |
| A — Full lift-and-shift | Fastest | Carries all legacy debt | A/B tests preserved |
| B — Greenfield + parity gate ✅ | +3 weeks | Clean architecture | A/B tests paused 2 wks |
| C — Hybrid (core lift-and-shift, new flows greenfield) | +1 week | Partial debt | A/B tests partially preserved |

Decision: Option B — Greenfield rebuild with feature parity gate + CX discovery sprint

Why product accepted: Staging data showed 15% improvement in Average Speed to Answer (ASA). TPM presented the data in the trade-off review. Product shifted from 'we need identical behavior' to 'we need equal or better outcomes.'

# 5.5  Trade-off Decision Summary

| # | Trade-off | Eng Wanted | Product Wanted | Decision | Owner |
| --- | --- | --- | --- | --- | --- |
| 1 | CNAM delivery | Defer — API unstable | Ship now — sales need it | Static now, RT in Q1 2025 | Marcus O. |
| 2 | Multi-region failover | Active-active | Single-region budget | Single-region + monitoring | Sarah C. |
| 3 | IVR approach | Greenfield rebuild | Lift-and-shift parity | Greenfield + parity gate | TPM |

Next section: Technical Debt Strategy →  program-management/technical-debt-register.md