PROJECT NORTH STAR

Section 6 — Technical Debt Strategy

Debt Register  ·  Impact Scoring  ·  P1 Playbooks  ·  Trend Analysis  ·  Stakeholder Comms

Version 2.1  ·  Sprint 14  ·  14 items  ·  3 P1 open

# 6.1  Technical Debt Philosophy

Technical debt on this program is tracked in the same Jira board as features, scored with the same priority system, and reviewed by the same stakeholders. Debt that is invisible is debt that doesn't get paid.

| Type | Definition | Example on NORTH STAR |
| --- | --- | --- |
| Intentional | Conscious short-cut with a plan to fix | SIP credentials in env vars (TD-001) — done to meet Wave 1 deadline |
| Accidental | Discovered after the fact — no one chose it | Terraform local state (TD-003) — prototype left in place |
| Architectural | Known design limitation, deferred | IVR flows not in version control (TD-004) — AWS Connect limitation |

## Debt Management Rules

- Every intentional debt item must be logged at creation — not after the fact

- P1 items are automatically added to the next sprint backlog — they cannot be ignored

- 15% sprint velocity is reserved for debt — ~6 of 42 story points per sprint

- Debt is never deferred more than 2 sprints without executive sign-off

- Each debt item carries an Impact Score = (Security Risk × 2) + (Delivery Risk × 2) − Effort

# 6.2  Technical Debt Register — Sprint 14

Total: 14 items  ·  P1 Open: 3  ·  P2 Open: 5  ·  Resolved: 6

| ID | Debt Item | Origin | Pri | Sec | Del | Eff | Score | Sprint | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TD-001 | Hardcoded SIP creds in Lambda env vars | Speed-to-ship W1 | P1 | 5 | 4 | 2 | 16 | S15 | In Progress |
| TD-002 | No automated rollback on DID port failure | Scope cut W1 | P1 | 1 | 5 | 3 | 11 | S16 | Planned |
| TD-003 | Terraform state in local backend | Prototype left | P1 | 2 | 5 | 1 | 13 | S15 | In Progress |
| TD-004 | IVR flows not version-controlled | AWS Connect limit | P2 | 2 | 4 | 5 | 7 | Q1 2025 | Backlog |
| TD-005 | No integration tests for Lambdas | Time pressure W1 | P2 | 1 | 3 | 3 | 5 | S17 | Planned |
| TD-006 | CloudWatch alarms not standardized | Incremental adds | P2 | 1 | 3 | 2 | 6 | S18 | Backlog |
| TD-007 | Real-time CNAM deferred — CSV only | Trade-off DR-005 | P2 | 1 | 4 | 5 | 7 | Q1 2025 | Backlog |
| TD-008 | DynamoDB on-demand only — no capacity plan | Not modeled W1 | P2 | 1 | 2 | 2 | 4 | S19 | Backlog |

Sec = Security Risk (1-5)  ·  Del = Delivery Risk (1-5)  ·  Eff = Effort (1-5)  ·  Score = (Sec×2)+(Del×2)−Eff

# 6.3  P1 Debt Detail

TD-001 — Hardcoded SIP Credentials in Lambda

| Field | Detail |
| --- | --- |
| What it is | Three Lambda functions have SIP trunk credentials stored as plaintext environment variables. Anyone with Lambda read access can retrieve live carrier credentials. |
| Why it happened | Wave 1 deadline pressure. Secrets Manager integration was descoped as a post-go-live fix. Never formally logged until Wave 1 retrospect. |
| Business impact | SOC 2 Type II finding. If unresolved before Q1 2025 audit, appears as open finding and could affect certification renewal. Financial exposure from credential theft. |
| Fix | Migrate all three Lambdas to retrieve credentials from AWS Secrets Manager at runtime. Scope IAM policies to restrict access to Lambda execution roles only. |
| Sprint target | Sprint 15 · Owner: Priya N. · Estimate: 3 days |

TD-002 — No Automated Rollback on DID Porting Failure

| Field | Detail |
| --- | --- |
| What it is | When a DID port fails mid-process, there is no automated recovery. Manual intervention takes 45 min to 4 hours depending on failure type. |
| Why it happened | Automated rollback was in Wave 1 scope. Descoped in Sprint 6 due to velocity shortfall. Formally logged at Sprint 6 retrospect. |
| Business impact | During Wave 2 (2,358 DIDs), a batch failure could leave 50-100 numbers in indeterminate state, creating a multi-hour customer impact window. |
| Fix | Lambda-based rollback function monitoring porting webhook events. DynamoDB state machine tracking port status and recovery actions. |
| Sprint target | Sprint 16 · Owner: Priya N. + James W. · Estimate: 5 days |

TD-003 — Terraform State in Local Backend

| Field | Detail |
| --- | --- |
| What it is | All AWS Connect infrastructure state is on Priya Nair's local machine. No remote backend, no locking, no team access. Another engineer running terraform apply would corrupt the state. |
| Why it happened | Infrastructure prototype became production without state migration. No formal handoff or review occurred before Wave 1 go-live. |
| Business impact | If Priya is unavailable (illness or departure — see R-006), no one else can safely modify infrastructure. Blocks CI/CD pipeline IaC validation. |
| Fix | Migrate to S3 remote backend with DynamoDB locking. See ADR-003 for full design. Highest ROI item on the board. |
| Sprint target | Sprint 15 · Owner: Priya N. · Estimate: 2 days |

# 6.4  Debt Trend

| Sprint | P1 Open | P2 Open | Resolved | Notes |
| --- | --- | --- | --- | --- |
| Sprint 10 | 3 | 6 | 1 | TD-010 resolved |
| Sprint 11 | 3 | 6 | 1 | TD-008 partial |
| Sprint 12 | 3 | 5 | 2 | TD-005, TD-006 partial |
| Sprint 13 | 3 | 5 | 0 | Wave 2 pressure — debt paused |
| Sprint 14 | 3 | 5 | 0 | Sprint 15: 43% velocity reserved for debt |

Zero debt resolved in Sprints 13-14 due to Wave 2 carrier delay consuming team capacity. Sprint 15 ring-fenced: 18 of 42 points (43%) for TD-001 and TD-003. Communicated to product in advance.

Next section: Scope Creep Control →  program-management/scope-change-log.md